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HEARING STATEMENT
IN RESPECT OF CONDITIONS AND LEGAL AGREEMENTS

On behalf of

THE MORAY COUNCIL

IN RELATION TO A PUBLIC LOCAL INQUIRY INTO APPLICATION UNDER

SECTION 36 OF THE 1989 ELECTRICITY ACT TO CONSTRUCT AND OPERATE A 59 TURBINE WINDFARM

(DORENELL WINDFARM)

By

INFINERGY ON LAND AT GLENFIDDICH ESTATE NEAR DUFFTOWN

Council Reference 08/01200/S36

My name is Aileen Scott.  I am a Principal Solicitor (Commercial and Conveyancing) at The Moray Council and am the Principal Legal Adviser to the Council’s Planning Service.

I will be representing The Moray Council at the forthcoming Planning Inquiry into the application under Section 36 of the 1989 Electricity Act for the proposed Dorenell Windfarm.

In terms of procedure notes produced by the Reporter the matter of conditions and any possible legal agreements required in respect of the proposed development are to be considered at a Hearing Session scheduled to take place during the period set aside for Hearing Sessions commencing at 10.00 am on Tuesday, 19 October 2010 and scheduled to last in the region of two to three days. The Council will be represented at the Hearing Session by a Planning Officer.
As the proposal is being considered under Section 36 of the 1989 Electricity Act, The Moray Council, as planning authority for the area affected by the proposal, has had the role of consultee.

As requested by the Reporter the Council has drawn up the proposed planning conditions, as set out in Schedule 1 to this Statement to address the impacts arising from the development . This is entirely without prejudice to the final determination of the application
Many of the conditions have been prepared in response to matters raised by other consultees such as SEPA, SNH and the Council’s Transportation Section. It is understood that both SEPA and SNH have the opportunity to submit further written representations for consideration by the Reporter and may wish to comment further on the suggested conditions prepared by the Council.

I am aware that the applicants through their solicitors - Biggart Baillie - have also produced a Hearing Statement on this topic and I have had sight of the same. I am aware that they have identified a list of issues to be covered by conditions but not drafted any actual conditions.

As outlined by the applicants in their Hearing Statement I can confirm, on behalf of the Council, that the Council as planning authority are willing to work with the applicants to progress a Joint Submission on conditions, to be lodged as a document by the due date to assist the Reporter at a Hearing Session on this topic so that the areas of agreement between the parties can be clearly identified and also the matters which are still in dispute.

The proposed planning conditions are as set out in Schedule I to this statement. This also includes relevant infomatives. Following further consideration of the draft conditions, together with review of conditions prepared by the applicant, and in preparation for any proposed Joint Submission on Conditions to be lodged to the Inquiry, additional or amended conditions and agreement may be identified.

In respect of suggested planning agreements the Council’s position is as follows.

Community Benefit:  From earlier discussion during the Council’s consideration of the proposal, the Council understands that there will be on offer a community fund.  The Council regards this as a matter between the applicant/developer and the local community and any agreement required to effect such a fund should be concluded between the relevant parties separately from the consideration being given to the planning merits of the proposed development.

SCHEDULE 1 

S.36 ELECTRICITY ACT 1989

TOWN & COUNTRY PLANNING (APPEALS) (SCOTLAND) REGULATIONS 2008 SCH.2

DORENELL WIND FARM 

Suggested draft conditions and reasons 

NOTE: This schedule is provided in accordance with the current appeal regulations and without prejudice to formal determination of the application for consent.

CONDITIONS AND REASONS

1
The development to which this permission relates must be begun not later than the expiration of 3 years beginning with the date on which this permission is granted.

Reason: The time limit condition is imposed in order to comply with the requirements of Section 58(I) of the Town and Country Planning (Scotland) Act 1997 as amended by the Planning etc. (Scotland) Act 2006.
2
Unless otherwise agreed with the Council as Planning Authority, the development hereby approved shall be carried out strictly in accordance with the approved plans and conditions.

Reason: In order to ensure that there are no unauthorised departures from the approved plans which could adversely affect the development or character and amenity of the surrounding properties and area.

3
Prior to work commencing on site the applicant shall complete the attached notification of initiation of development and submit it to the Council as planning authority.

Reason: To ensure that the Council, as planning authority is aware that the development is about to commence and any suspensive conditions can be followed up.

4
Upon completion of the development or as soon as practicable after doing so the attached notification of completion of development shall be completed and submitted to the Council as planning authority.

Reason: To ensure that the Council as planning authority is aware that the development is complete and is able to follow up conditions

5
This permission is for the period of 25 years from the date that the electricity from the development is first connected to the national grid, such date to be notified to the Council, as Planning Authority within one month of the date of such connection. Within 12 months of the end of the 25 year period the wind turbines and ancillary equipment shall be dismantled to ground level and removed from the site and the land shall be restored in accordance with a decommissioning, restoration and after-care scheme to be submitted to and approved by the Council, as planning authority, not later than one year prior to the expiry of the 25 year period referred to above.

Reason: In order to retain control over the use of the site and to ensure that at the end of the operating period, the site is restored to an agreed condition.

6
No development shall commence until an amended Drainage Management Plan for the construction compound, to include details of the vehicle wash bay and batching plant, has been submitted to and approved by the Council, as planning authority, in consultation with SEPA.

Reason: To ensure an acceptable form of development in terms of drainage and pollution prevention.

7
No development shall commence until details for the method of water abstraction/impoundment for the construction compound have been submitted to and approved by the Council, as planning authority in consultation with SEPA.

Reason: To ensure an acceptable form of development in terms of water abstraction.

8
No development shall commence on site until details of a construction method statement has been submitted to and approved by the Council, as planning authority.  The statement shall include details of all on-site construction, drainage, mitigation, restoration/reinstatement work and timescales and specifically the statement shall address the following works:

i) Public Road Works (Widening/Junction Improvement/Entrance Works);

ii) Site Tracks;

iii) Watercourse crossings (where proposed);

iv) Construction Compound;

v) Crane Pads;

vi) Cable Trenches;

vii) Foundation Works, including working widths;

viii) Substation and control building;

ix) Anemometry masts;

x) Oil storage compound and bunding;

xi) Cleaning of site entrances and the adjacent public highway;

xii) Post construction restoration/reinstatement of the working areas, including approval of seed mixtures.

Reason: To ensure that the development is carried out in a manner that protects the general public, wider public amenity and the environment.

9
No development shall commence until details regarding a plan for the management of abnormal loads has been submitted to and approved by the Council as planning authority in consultation with Moray Council Transportation (Traffic) and Transport Scotland (as appropriate).  The Plan shall include the following:

i) a detailed survey of the chosen route for delivery vehicles;

ii) the locations of structures, e.g. bridges and street furniture affected by any construction and abnormal load vehicle movements;

iii) the location, design construction and timescale for provision of any road improvements/strengthening required or proposed;

iv) details of the arrangements including timescale to undertake and monitor abnormal load trial runs prior to commencement of construction;

v) in the event of the trial runs identifying any restrictions not identified in any earlier detailed survey, details of the location, design construction and timescale for the provision of any additional road improvements/strengthening required or proposed to be carried out;

vi) details of the number, spacing, location and timescale for all abnormal load passing places/on-coming vehicle holding areas to be provided and constructed, in accordance with The Moray Council specification, including holding areas for on-coming traffic to be provided along the A920 between the A920/A941 and The Moray Council boundary;

vii) details to demonstrate that only single abnormal loads shall be transported along the A941 between the A920;

viii) details regarding the location, design construction (to The Moray Council specification) and timescale for provision of a holding area for the other vehicles in convoy to be provided near the A920/A941 junction; 

ix) details regarding the location and design construction (in accordance with the Moray Council specification) for the widening of the A941 at the top of the hill at Laggan for unrestricted vehicle passing of abnormal loads and other construction traffic;

x) details for holding areas for on-coming traffic to be provided along the A921 between the A920/A941 and The Moray Council boundary, the latter being required or proposed as a result of any abnormal trial run being carried out; 

and

xi) thereafter, the development shall be carried out in accordance with the approved details prior to any timber extraction or delivery of materials to the site, including provision of all road improvement/strengthening works prior to any construction traffic movements, in particular abnormal load traffic.

Reason: In the interests of road safety and to enable a safe and suitable access for large construction vehicles to/from the site.

10
No development shall commence until details regarding a Traffic Management Plan have been submitted to and approved by the Council, as planning authority in consultation with Moray Council Transportation (Traffic) and Transport Scotland (as appropriate). The Plan shall include the following:

i) details to show the method of dealing with large delivery vehicles to include vehicle swept path analysis; 

ii) the arrangements to undertake verge hardening at the A920/A941 junction to accommodate the wide turning circle of the abnormal load vehicles transporting turbine components over the junction areas, with dropped kerbs to be installed during the construction period to enable over-running onto the hardened verge and post- construction, the existing 254mm x 127mm h.p.c.c. kerbs must be reinstated at the junction;

iii) the methods of marshalling and manoeuvring at junctions on the public road network;

iv) details of all heavy construction traffic routes to/from the site and demonstrate that no heavy construction traffic shall access the site from the A941 south;

v) the arrangements to undertake and submit before and after video surveys of the proposed delivery route(s) together with confirmation to make good any damage caused to the road network, including the verge as a result of construction traffic and passing vehicles;

vi) details regarding the location(s), design construction (to The Moray Council specification)and timescale for provision of all inter-visible passing places and on-coming vehicle holding areas to accommodate construction traffic, turbine delivery vehicles and on-coming traffic required or proposed to be provided along the A941 between the A920/A941 and the site access junction;

vii) details regarding the arrangements including the location(s) and timescale for the provision of day-time traffic signal controlled one-way working to be provided on the narrow section of the A941 road between Laggan and Bridgehaugh.  The signal control shall be operational for the duration of the construction and decommissioning of the wind turbines;

viii) details of a scheme regarding the location and type of road signage to be provided at the proposed access junction to the site onto the A941; 

ix) details including the location and duration for a temporary speed limit to be provided at the site access together with identification of all relevant or required statutory procedures to be promoted for the temporary speed limit.  The required speed limit shall be in force for the duration of the construction and decommissioning of the wind farm; 

and

x) thereafter, the development shall be carried out in accordance with the approved details prior to any timber extraction or delivery of materials to the  site.

Reason: In the interests of road safety and to enable a safe and suitable access for vehicles to/from the site.

11
The new access junction to the site onto the A941 shall have visibility splays of 4.5m x 120m, and shall be kerbed to a radius of 15m using 254mm x 127mm h.p.c.c. kerbs. 

Reason: In the interests of road safety and to enable a safe and suitable access. 

12
Prior to first use of the access commencing, the proposed new access roadway to the A941 from the site shall be surfaced using Hot Rolled Asphalt for a minimum distance of 30m or the length of the longest vehicle and load, whichever is the greater, if the access is not to be constructed to an adoptable road standard.

Reason: In the interests of road safety and to enable a safe and suitable access.

13
Prior to first use of the access commencing, a 50m length of Hot Rolled Asphalt shall be provided on the A941 (i.e. 25m either side of the centreline of the new junction) and the A941 shall be widened to at least 6.0m over the length of the Hot Rolled Asphalt section of the road at the new access junction including appropriate tapers, such that the delivery/construction vehicles do not have to mount the verges when negotiating the access junction.

Reason: In the interests of road safety and to enable a safe and suitable access.

14
No water shall be permitted to drain, or loose material be carried onto the public footway/carriageway.

Reason: In the interests of road safety.

15
Any existing ditch, watercourse or drain under the site access or passing places or holding areas shall be re-routed or piped using a suitable diameter of pipe, in accordance with details to be submitted to and approved by the Council, as planning authority in consultation with Moray Council Transportation (Roads Maintenance Manager).  Any pipe shall be laid to self-cleansing gradient.

Reason: In the interests of road safety.

16
If significant unsuspected contamination is found, then all work shall cease until and appropriate investigation to determine the nature, extent and potential impacts of the contamination has been undertaken and a remediation method statement agreed with the Council as Planning Authority.

Reason: In order to safeguard the health and safety of the occupants of the property from the effects of harmful ground contamination.

17
No development shall commence until details of a finalised Health and Safety Environment Management Systems (HSEMS) have been submitted to and approved by the Council, as planning authority in consultation with Moray Council Transportation, SEPA, SNH and others (as appropriate) where: 

i) the HSEMS shall be based on the details included in the Environmental Statement (Volume 2, Chapter 25), as submitted with the application and include all finalised Environmental Management Plans (for example, Habitat Management Plan, etc.) and Construction Method Statements (for example, Peat Management Plan, Pollution Incident Response Plan, etc) identified therein;

ii) the finalised management plans and statements to be submitted shall be based on a schedule which shall previously have been submitted to and approved by the Council, as planning authority to confirm/identify all management plans and statements to be prepared, timescales for preparation/submission and all agencies to be consulted prior to finalisation of each document;

iii) the required finalised management plans and statements as submitted to the Council, as planning authority shall be accompanied by written confirmation of acceptance of the finalised documents from all agencies consulted on the proposal;  

iv) identify all mitigation measures to be adopted and implemented which shall be based on the details included in the Environmental Statement (Volume 2, Chapter 25, Tables 25.1 and .2; 

and

v) thereafter the development shall be carried out in accordance with the approved details.

Reason: To ensure an acceptable form of development with a system of documents designed to guide/aid the implementation of the development hereby consented and address all aspects of site work that might impact on the environment and identify and ensure that all appropriate mitigation measures are implemented to minimise an adverse impacts associated with the development.

18
No turbine shall be erected until details have been submitted to and approved in writing by the Council as planning authority in consultation with the operator, NATS (En Route) plc. regarding the following:

i) a Statement of Common Understanding, setting out requirements for mitigation and principles to govern the development;

ii) an Operator Mitigation Scheme, setting out all obligations including measures to mitigate, at all times, the impact of the development on the primary radar and associated air traffic management operations of NATS.

Reason: To ensure an acceptable form of development in the interests of safeguarding radar and air traffic interests.

19
No turbine shall be erected until all obligations contained within the approved Operator Mitigation Scheme (other than on-going obligations) have been fully implemented and the development shall thereafter, be operated fully in accordance with all on-going obligations contained within the Operator Radar Mitigation Scheme details of which shall be included within the Operator Mitigation Scheme.

Reason: To ensure an acceptable form of development in the interests of safeguarding radar and air traffic interests.

20
Prior to the delivery to the site, full details of the wind turbines including the make, model, design, power rating and sound power levels of wind turbine to be used on site shall be submitted to and approved by the Council as planning authority.  As part of the required details, the applicant shall secure and submit a warranty from the turbine supplier and/or manufacturer for the absence of tonality of the turbine, as determined in accordance with a recognised standard together with a copy of the standard detailing the assessment method.  In the absence of such warranty, a tonal penalty of 5dB will be assumed and noise levels specified in condition 22 below will be reduced by 5dB.

Reason: To ensure an acceptable form of development in the interests of amenity of the development and its impact upon surrounding noise sensitive property

21
The wind farm operator shall log wind speed and wind direction data continually and shall retain the data, which has been obtained for a period of no less than the previous 12 months. The data shall include the average wind speed in metres per second for each 10 minute period. The wind speed and wind direction data shall be made available to the Planning Authority on request.

Reason: To ensure that proper records are kept to enable an assessment of the operation of the development.

22
At wind speeds not exceeding 10 metres per second, as measured or calculated at a height of 10m above ground level at the nearest wind monitoring mast, the Wind Turbine Noise Level at any dwelling or other noise sensitive premises shall not exceed an LA90, 10min of 35dB.  This condition shall only apply to dwellings or other noise sensitive premises existing at the date of the consent hereby issued and the method of assessment of noise levels shall be in accordance with “ETSU-R-97. The Assessment and Rating of Noise from Wind Farms”.

Reason: In the interests of the amenity of the development and surrounding noise sensitive property and to mitigate the impact of noise disturbance activity likely to be associated with the impact of the development.

23
At the request of the Council as planning authority, following any complaint received by The Moray Council relating to noise emissions from the Wind Turbines, 

i) the wind turbine operator shall measure (at its own expense) the level of noise emissions from the Wind Turbines (inclusive of existing background noise) using an La90 index over a minimum of 20 periods, each of 10 minutes duration.  At least 10 measurements shall be made at wind speeds between the wind speed specified by the Council and a wind speed not less than 2 metres per second below that specified by the Council.  Measurements of noise emissions shall, as far as is practically possible, be made in consecutive 10 minute periods provided that they fall within the wind speed range as defined in this condition.  The results of the measurements of levels of noise emissions shall be submitted to the Council, as planning authority together with all required or proposed measures to be carried out to mitigate noise levels; and 

ii) where required by the Council, as planning authority, the wind turbine operator shall carry out an assessment for tonal noise in accordance with the procedure recommended in Chapter 6 of the document “The Assessment and Rating of Noise from Wind Farms (ETSU-R-97)” i.e. the procedure based on Joint Nordic Method.  The results of the assessment for tonal noise shall be submitted to the Council, as planning authority together with all required or proposed measures to be carried out to mitigate noise levels;

iii) Where the tone level above audibility is greater than 2dB a tonal penalty shall be applied to permitted noise levels, in accordance with Figure 16 of the assessment document noted above; so that the permitted levels specified in conditions 20 and 22 above will be reduced by the tonal penalty.

Reason: In the interests of the amenity of the development and surrounding noise sensitive property and to reduce or mitigate the impact of noise disturbance activity likely to be associated with the impact of the development and that any problems arising are dealt with timeously in the interests of local residential amenity.
24
Measurements made in accordance with the provisions of conditions 23, in order to demonstrate compliance with the requirements of conditions 20 and 22, shall be correlated with wind speeds (Condition 21).

Reason: In the interests of the amenity of the development and surrounding noise sensitive property and to ensure that an appropriate methodology for the assessment of noise emissions is undertaken.
25
Construction activities associated with the development, including access to the site by vehicles and vehicle movements on the site, shall be permitted between 0700 to 1900 hours Monday – Friday, and 0800 to 1800 hours on Saturdays.  Any works required outwith those times shall not be permitted unless prior written details are provided  in the Construction Method Statement.

Reason: In order to protect public and residential amenity in the area.

26
Ground vibration as a result of blasting operations to form the borrow pit at the site shall not exceed a peak particle velocity of 10mms-1 in 95% of all blasts, and no individual blast shall exceed a peak particle velocity of 12mms-1 as measured at vibration sensitive buildings.  The measurement shall be the maximum of 3 mutually perpendicular directions taken at the ground surface at any vibration sensitive building.

Reason: In the interests of the amenity of the development and surrounding ground vibration sensitive property and to reduce or mitigate the impact of vibration disturbance activity likely to be associated with the impact of the development.
27
At the request of the Council as planning authority, following any complaint received by the Council relating to vibration from blasting operations to form the borrow pit, the developer shall measure at its own expense ground vibration to ensure compliance with the above condition.  The results of the measurements of levels of ground vibration shall be submitted to the Council, as planning authority together with all required or proposed measures to be carried out to mitigate vibration levels.

Reason: In the interests of the amenity of the development and surrounding vibration sensitive property and to reduce or mitigate the impact of vibration disturbance activity likely to be associated with the impact of the development and that any problems arising are dealt with timeously in the interests of local residential amenity.

28
No development shall commence until details have been submitted to and approved by the Council as planning authority regarding the colours/external finishes of the turbines and all ancillary elements (including access tracks, transformers, substation and control buildings, compound and fencing, etc)

Reason: To ensure that the finishes are satisfactory, in the interests of visual amenity and the appearance of the development and the surrounding area.

29
At the request of the Council, as planning authority the developer shall provide information concerning the supply of electricity to the grid from any turbine.  If any turbine fails to supply electricity to the grid for a continuous period of 6 months then, unless otherwise agreed in writing with the Council as planning authority, a scheme for the decommissioning and removal of the wind turbine and any other ancillary equipment above ground level relating solely to that turbine, and including the restoration of the site involved shall be submitted to the Council, as planning authority within 3 months of the end of the 6 month period of non-supply and thereafter be carried out in accordance with the scheme approved.

Reason: To ensure that the turbines operate as intended and that any turbine(s) which become non-operational for an extended period are removed from the site.

30
The rotors of the turbines shall all rotate in the same direction.

Reason: To avoid potential visual discomfort from the sight of contra-rotating rotors.
31
All electricity and other service cables between the turbines and the substation/control building shall be placed underground.

Reason: To protect the visual amenity of the area from further impact.

32
The temporary contractor’s site compound shall be provided at the location identified on the approved plans and at no other location without the prior written consent of the Council, as planning authority and

i) prior to the use of the compound first commencing, the area of the compound shall be clearly defined using temporary fencing or similar;

ii) no compound activity shall take place outwith the defined area, including all site accommodation, movement and storage of construction vehicles including any mobile of fixed plant used to process material on site; and 

iii) upon completion of construction works or commissioning of the last turbine erected, whichever is the sooner, the temporary compound shall cease and the land shall be restored/re-instated to its existing condition in accordance with approved details of the arrangements including timescale for restoration/reinstatement of the land to be submitted not less than 4 weeks prior to the cessation of the use of the land as a temporary compound.

Reason: To ensure a satisfactory form of development in the interests of the amenity and appearance of the locality, including details lacking from the submission, the temporary compound being required solely for the construction phase of the development and to allow the site to revert to its existing condition.

33
No development shall commence until a construction method statement for any borrow pit required or proposed as part of the development has been submitted to and approved by the Council, as planning authority.  The method statement shall include:

i) a location plan showing the extent of the working, details regarding the depth of excavation with finished levels related to existing ground levels, the locations and heights of all material to be stockpiled on site; details of type of machinery to be used within the borrow pit, and the means of enclosure;

ii) the arrangements for the restoration/re-instatement and aftercare of the site including removal of fencing, details of any ground works to be carried out with finished levels related to existing or excavated ground levels, seeding and planting arrangements, etc.

iii) in the event of blasting being required, details of times and dates of such activity; 

and

iv) thereafter, the operation of the borrow pit shall be carried out in accordance with the approved details.

Reason: To ensure that the development is carried out in a manner which protects the general public, wider public amenity and the environment including proposals for the restoration/reinstatement of the site once borrow pit activity ceases.

34
No development shall commence until details of a decommissioning survey have been submitted to and approved in writing by the Council, as planning authority in consultation with SEPA and SNH.  The details shall include the following;

i) the timescales for decommissioning;

ii) the intended survey programme in relation to this; and

iii) the species to be surveyed and the methods used to identify their presence; 

and

iv) thereafter, the decommissioning of the site shall be carried out in accordance with the approved survey details, including proposal to mitigate the impact of decommissioning on all natural heritage interests. 

Reason: In order to record and ensure the protection of protected species.

35
No development shall commence until details relating to the appointment and role of an Ecological Clerk of Works to oversee the construction, operation and decommissioning of the wind farm have been submitted to and approved by the Council as planning authority in consultation with SEPA and SNH.

Reason: In order to ensure the regular monitoring, recording and protection of natural heritage interests.
36
No development shall commence until details of all anticipated fixed and mobile plant have been submitted to and approved in writing by the Council as planning authority.

Reason: In order to ensure an acceptable form of development and the protection of the environment

37
No development shall commence until details of an Access Management and Recreation Plan for the development have been submitted to and approved by the Council, as planning authority.  This plan shall include the following:

i) the location, design and layout of all proposed or required car parking facilities;

ii) the location, design and layout of access points and path networks required or proposed for pedestrians and cyclists; and

iii) the location and details of any interpretative/information facilities and any other visitor facilities to be provided;

iv) details of the arrangements required or proposed for the provision of access rights and works including their location and design to enable or improve access e.g. paths, signage, footbridges, etc both within the site and connections to the existing path network outwith the site   

and

v) thereafter, the development shall be carried out in accordance with the approved details.

Reason: In order to ensure an appropriate level if access to the site for recreation and amenity purposes.

Informatives (i.e. additional information offered as advice to the applicant/developer)

THE TRANSPORTATION MANAGER, DIRECT SERVICES, ACADEMY STREEET, ELGIN has commented that:-

· No building materials/scaffolding/builder’s skip shall obstruct the public road (including footpaths) without permission from the Roads Authority.

· Any construction work associated with the public road network will require Road Construction Consent (RCC) under S.21 of the Roads (Scotland) Act 1984.

· The applicants shall be responsible for any necessary diversion of any utilities or drainage present at the locations where works are to be undertaken.

· The applicants shall meet all costs of improvements to road infrastructure, which are required as a result of the development.

· The applicants shall meet all the costs of removal and re-erection of road signage, which are required as a result of the delivery of the abnormal loads.

· The applicant shall be responsible for ensuring that surface/ground water does not run from the public road into his property.

· The applicant shall ensure that their operations do not adversely affect any Public Utilities, which should be contacted prior to commencement of operations.

· The applicants shall free and relieve the Roads Authority from any claims arising out of his operations on the road or extension to the road.

· The Transportation Manager must always be contacted before any works commence. This includes any temporary access, which should be agreed with the Roads Authority prior to work commencing on it.

· No retaining structures or embankments shall be constructed along the edge of the road, whether retaining the public road or ground adjoining the public road without prior consultation and agreement of the Roads Authority.

· The full details of the temporary Road Traffic Order required for the temporary speed limit shall be agreed with Moray Council Transportation (Traffic). 

· The costs associated with the promotion and implementation of the temporary Road Traffic Order will be met by the applicant.

· A road opening permit for the day time traffic signal controlled one-way working between Laggan and Bridgehaugh is required from Moray Council Transportation (Traffic).

· Representatives from Aberdeenshire and Moray Council Transportation (Traffic), the Trunk Road Authority and Grampian Police must be invited to any abnormal load trial run.

· A scheme for appropriate road signs at the proposed access junction shall be submitted for approval by Moray Council Transportation (Traffic).

· The location(s) of the holding areas along the A920, between the A920/A941 and The Moray Council boundary, shall be agreed during the trial run with The Moray Council (Traffic) and Grampian Police.

· The applicant shall demonstrate that the applicant has or can obtain control at location(s) for the holding areas agreed by Moray Council Transportation (Traffic) and constructed in accordance with The Moray council specification.

THE ENVIRONMENTAL HEALTH MANAGER, DEVELOPMENT SERVICES, has commented that:-

· The wind farm operator should ensure appropriate precautions are taken to ensure construction operations do not affect the quality and/or quantity of private water supplies, in terms of the Private Water Supplies (Scotland) Regulations 2006.
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