Insert School name here

PARK SMART ACTION PLAN

*Prior to week one the school must have requested the banners and Pop up models and have arrangements in place for delivery.

Describe your baseline situation here and what you have done previously to deal with it. Eg: we have asked parents not to park at the gates in many school newsletters….. etc

| Park smart Week One – Raising Awareness week |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Target | Personnel Involved | Resources/ Support | Timescale |
| Survey pupils on how they travel to school | To gather a baseline. Visit each of the classrooms and do a count. | JRSO team JRSO Co-ordinator | Travel Tracker / WOW | Week 1 Day 1 |
| To have a school traffic count at peak times | To gather a baseline. Carried out at the school gates. | JRSO team JRSO Co-ordinator | Traffic Count Template | Week 1 Over 3 days |
| Have a Park Smart Assembly | To inform other pupils of the reasons for Park Smart – both safety and health – launch competitions | Whole school led by JRSO Team | Assembly ideas, competition ides. Invite Living Streets, Police Scotland etc | During week 1 |
| Send parents’ letter/ footprint pledge home to be completed and returned. | To collect information from parents of their commitment to help ease congestion over the following weeks | JRSO team JRSO Co-ordinator |  | During week 1 |
| Record traffic count results For comparison in Week 3 |  | JRSO Co-ordinator |  | Week 1/3 |

| Park smart Week Two – Enforcement week |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Target | Personnel Involved | Resources/ Support | Timescale |
| Display the banner and Pop up figures at the gates to remind parents not to park or drop off there. School Support Officer | To remind parents that the Park Smart campaign in now taking place and that if they drive then they should park away from the gates. | School staff and JRSO co-ordinator | Banner and Popup figures are on the premises | Day 1 Week 2 |
| Display Parent Pledges in School To make a colourful display in school of all the pledges |  | School Staff |  | By end of week 2 |
| Ask Police Scotland to visit school at key times of day. | To deal with parents who are still dropping off or parking in a dangerous manner | Head Teacher/ Police Scotland | Request visits for your school during this week | In week 1 for Week 2 |
| Tweet using #MorayParkSmart | To let the public know what is going on | School contact for Twitter account | Tweet photos of your Traffic or Pupil counts, display boards and banners etc. | Week 1 and 2 |

| Park smart Week Three – Evaluation week |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Target | Personnel Involved | Resources/ Support | Timescale |
| Continue to display banner and Pop up figures at the gates | To remind parents that the Park Smart campaign is still taking place and that if they drive then they should park away from the gates. | School staff and JRSO co-ordinator | Banner and Popup figures are on the premises |  |
| Carry out a 2nd Traffic Count at the gates | To find out if your Park Smart campaign has made a difference. | JRSO Team JRSO Co-ordinator | Traffic Count 2 Template | Week 3 over 2-3 days |
| 2nd class Survey for pupils on how they travel to school | To find out if your Park Smart campaign has made a difference | JRSO Team JRSO Co-ordinator | Travel Tracker/ WOW | Towards end of week 3 |
| JRSO Assembly | To share results with whole school on the difference the Park Smart campaign has made | Whole school led by JRSO Team | Celebrate success |  |

| Park smart - Ongoing |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Target | Personnel Involved | Resources/ Support | Timescale |
| The way forward! | Update School Travel Action Plan | JRSO Co-ordinator/Moray Council Sustainable travel officer | Update your travel plan to include dates to repeat Park smart at least once a term/ year etc. | ongoing |